## Form 3
(Form 3 )
Annual Development Plan - 2021
Provincial Specific Development Grant (PSDG)
Ministry - Ministry of Provincial Roads, Rural Infrastructure, Tourism, Sports and Youth Affairs.
Department / Agency - Ministry of Provincial Road
Sector -Provincial Roads |  |  | Total budget for the sector (Rs. Mn) - 560.60
S.No | Component and Budget (Rs. Mn) | SDG Target No. | Sub Component and Budget (Rs.Mn) | Outcomes |  |  |  | Broad Activity Area | Output | Budget (Rs.Mn)
|  |  |  | KPIs | Baseline | Target
[5 empty] | 2016 | 2021 | 2022
1 | Establishment and operation of a quality road network in the province (Rs.Mn 555.60) | 3.6,9.1,9.2,9.3 | 1.1 Road rehabilitation (Rs.Mn 337.50) | No. of roads | 420 | 62 | 64 | 1.1.1.Road Renovation | 80 km renovated | 337.5
|  |  |  | No. of Km | 204.54 | 80 | 100
|  |  | 1.2 Road improvement (Rs.Mn175.10) | No. of roads | 110 | 38 | 40 | 1.2.1.Construction of structures | 38Km nos roads improved | 175.1
|  |  | 1.3 Road safety improvement (Rs.Mn 14.00) | Unauthorized incidents | 50 | 1 | 10 | 1.3.1 accident mitigation settings | roads improved | 6
[6 empty] | 8 | 16 | 1.3.2. Sign board | Sign board established | 4
[6 empty] | 16 | 24 | 1.3.3. Pedestrian crossing | Made pedestrian crossing | 4
|  |  | 1.4 Reconstruction of major structures (Rs.Mn29.00) | No,of structures | 53 | 10 | 16 | 1.4 Renovation of major structures | 10 nos structures renovated | 29
2 | Enhancement of planning and management (Rs.Mn 5.00) | 9.1 | 2.1 Maintaining existing capital assets & provision of new assets (Rs . Mn 5) | Unauthorized incidents | 50 | 12 | 11 | Providing equipments for road development | Equipments provided | 5
Total | [9 empty] | 560.6

## form 3a
Annex 04
(Form 3a)
Annual Development Plan -2021
Provincial Specific Development Grant (PSDG)
Ministry - Ministry of Provincial Roads, Rural Infrastructure, Tourism, Sports and Youth Affairs.
Department / Agency -
Sector - Provincial Roads |  |  | Total Budget for the sector (Rs. Mn.560.60)
Component 1 - |  |  | Total Budget for the component 1 (Rs. Mn.555.60)
Establishment and Operation of a quality Road network in the Province
Sub Component and Budget (Rs.Mn) | Broad activity area and Budget (Rs.Mn) | List of Activity |  | Budget (Rs.Mn)
|  |  |  | Ratnapura | Kegalle |  | District 3 |  |  | DS | ED
1.1 Road Rehabilitation (Rs.Mn 337.50) | 1.1.1.Rehabilitation of road surface (Rs.Mn 337.50) | 1 | Concreting shoulders of Palawela Kehelowitigama road (0.000-2.000Km) | 4 |  |  |  | T / Governor Pel E.E |  | Elapatha |  | 89.41
|  | 2 | Concreting shoulders of Kotamulla Dimiyawa road (5.000-8.000Km) | 4 |  |  |  | Bala E.E |  | Elapatha |  | 89.09
|  | 3 | Concreting shoulders & constructing side walls of Wellawala Gurubewilagama road (0.00-1.00Km) | 3 | [5 empty] | Ratnapura
|  | 4 | Concreting shoulders & expanding culverts of Paleegala road (0.00-3.00Km) | 3 |  |  |  | Emb E.E |  | Eheliyagoda
|  | 5 | Concreting shoulders & expanding culverts of Minnana Uduwaka road (0.00-6.00Km) | 5 |  | 3.5 |  | Keg E,E |  | Eheliyagoda
|  | 6 | Concreting shoulders of Minnana Wilegoda road (0.00-6.00Km) | 4 |  | 3.5 |  | Keg E,E |  | Eheliyagoda
|  | 7 | Concreting shoulders & expanding culverts of Moragala Bulugahapitiya road (0.00-1.50Km) | 2 |  | 0.25 |  | Dehi E.E |  | Eheliyagoda
|  | 8 | Concreting shoulders & expanding culverts of Parakaduwa Dikdeniya road (0.00-3.00Km) | 3 |  | 3 |  | Dehi E.E |  | Eheliyagoda
|  | 9 | Concreting shoulders & expanding culverts of Ekneligoda Guruluwana road (0.00-4.00Km) | 3 |  | 3 |  | Govener Dehi E.E |  | Kuruwita
|  | 10 | Concreting shoulders of Kuruwita Erathna road (9.20-12.00Km) | 3 | [5 empty] | Kuruwita
|  | 11 | Concreting adawikanda Warnagala road (3.50-4.00Km) | 6 |  | 4 |  | Dehi E.E |  | Kuruwita
|  | 12 | Constructing drain & expanding road of Watapotha Manandola (1.00-2.00Km) 1st Stage | 8 | [5 empty] | Kalawana
|  | 13 | Constructing drain & expanding road of Watapotha Manandola (2.00-3.40Km) 2nd Stage | 8
|  | 14 | Constructing drain & expanding road of Watapotha Manandola (3.40-4.50Km) 3rd Stage | 8
|  | 15 | Concreting shoulders in necessary places of Hangamuwa Karawita road | 5
|  | 16 | Improvements of Rajjuruwaththa Pimbura road (0.00-1.30Km) | 10
|  | 17 | Improvements of Dela Erabadda road (3.90-5.90Km) | 7
|  | 18 | Improvements of Kolambagama Pahalakanda road (2.0Km) | 7
|  | 19 | Paving interlocking of Nammuniyawaththa Madabaddara road (0.30-2.50Km) | 7
|  | 20 | Paving interlocking of Waththahena Doloswala road | 5
|  | 21 | Concreting road surface & constructing both sides of Atalla Gamekanda road | 5
|  | 22 | Improvement of Konkatuwa Welipothayaya road | 10 | [5 empty] | Embilipitiya
|  | 23 | Improvement of Kolabageara Panahaduwa road(from 7.2Km) | 12
|  | 24 | Improvement of Miriswelpotha Adoluwa road(from1.2Km) | 10
|  | 25 | Improvement of C.P.De. Silva road | 5
|  | 26 | Improvement of Guruara Thalagahawela road | 5
|  | 27 | Improvement of Morahela Amupitiya road (5.02Km) | 10 | [5 empty] | Imbulpe
|  | 28 | Improvement of Aluthnuwara Nelliwala road (3.08Km) | 8 | [5 empty] | Imbulpe
|  | 29 | Concreting shoulders & repair road surface in Gurubawila road (9.73Km) | 9 | [5 empty] | Imbulpe
|  | 30 | Improvement of Iepathwela Pidaligannawala Maddegama road (2.5 Km) | 5.5 | [5 empty] | Imbulpe
|  | 31 | Improvement of Aluthnuwara Passaramulla road (0.00-0.9 Km) | 7.5 | [5 empty] | Imbulpe
|  | 32 | Improvement of Galagama Borangamuwa road (6.00-10.10Km) | 7.5 | [5 empty] | Imbulpe
|  | 33 | Improvnment of Halpe Weheragoda road (0.0-4.20Km) | 3 | [5 empty] | Imbulpe
|  | 34 | Concreting shoulders of Seethagala Udakanda road (0.00-2.50Km) | 2.5 |  |  |  | Bala E.E |  | Balangoda |  | 89.09
|  | 35 | Development of from Ellawaththa juntion to Welekumbura juntion | 2.5 |  |  |  | Bala E.E |  | Balangoda |  | 89.09
|  | 36 | Improvenment of road surface at Naranbedda Dunukewala road |  | 6 |  |  |  |  | Rambukkana
|  | 37 | Construction of shoulders at Molagoda Mahinthenna road |  | 4 |  |  |  |  | Rambukkana
|  | 38 | Construction of necessary places at Ayagama Aluthnuwara road |  | 4 |  |  |  |  | Mawanella
|  | 39 | Construction of road surface & shoulders in Balawathgama Meepitiya Waduwawella |  | 4 |  |  |  |  | Mawanella
|  | 40 | Construction of road surface Udugama Alubohinna road |  | 2 |  |  |  |  | Rambukkana
|  | 41 | Concreting Abadeniya Labutuwa road |  | 4 |  |  |  |  | Aranayaka
|  | 42 | Improvnment of Kegalle North Cuircle road (0.50-2.85Km) |  | 10 |  |  |  |  | Kegalle
|  | 43 | Improvnment of Udabogala road (0.00-1.00Km) |  | 4 |  |  |  |  | Kegalle
|  | 44 | Improvnment of Pahala Bogala road (0.00-1.00Km) |  | 3 |  |  |  |  | Kegalle
|  | 45 | Improvnment of Makura Kawudugama road (0.00-1.00Km) |  | 3 |  |  |  |  | Kegalle
|  | 46 | Improvnment of Makura Vihara road (0.00-1.20Km) |  | 4 |  |  |  |  | Kegalle
|  | 47 | Improvnment of Mabopitiya Thalagahamadiththa road (0.40-1.90Km) |  | 4 |  |  |  |  | Kegalle
|  | 48 | Improvnment of Eragama Parambewaththa road (1.00-2.00Km) |  | 4 |  |  |  |  | Kegalle
|  | 49 | Improvnment of Ganithapura Ethnawala road (1.40-2.60Km) |  | 4 |  |  |  |  | Warakapola
|  | 50 | Improvnment of Kongoda Palamure Niyadurupola road (1.00-3.00Km) |  | 7 |  |  |  |  | Warakapola
|  | 51 | Improvnment of Mangedara Hunuwala Paspolakanda road (1.00-7.00Km) |  | 10 |  |  |  |  | Warakapola
|  | 52 | Improvnment of Kabagamuwa Rangalla road (0.00-1.00Km) |  | 4 |  |  |  |  | Bulathkohupitiya
|  | 53 | Construction of shoulders in necessary places at Galapitamada Athudakanda road |  | 5 |  |  |  |  | Ruwanwella
|  | 54 | Concreting Anhettigama Kehelwala road |  | 6 |  |  |  |  | Deraniyagala
|  | 55 | Concreting necessary places in Maliboda Orupeella road |  | 7 |  |  |  |  | Deraniyagala
|  | 56 | Concreting Miyanawita Dehigasdeniya road |  | 4 |  |  |  |  | Deraniyagala
|  | 57 | Construction of shoulders at Nawatalavent Halgolla road(6 - 11.5Km) |  | 4 |  |  |  |  | Yatiyanthota
|  | 58 | Development of Rakwana Sringwood Nawinna road(3.50-4.70Km) | 3 | [5 empty] | Pelmadulla
|  | 59 | Development of Welagepola Makadura road (0.00-1.50Km) | 6
|  | 60 | Development of Endana Nahalwathura road (4.00-5.24Km) | 3
|  | 61 | Development of Weladura Bungiriya Pothuwil road (0.00-1.00Km) | 5
|  | 62 | Concreting shoulders in Kahawaththa Kattange road (0.00-6.23Km) | 6
1.2 Road improvement (Rs.Mn 175.10) | 1.2.1. Construction of structures(drains, culverts) (Rs.Mn 175.10) | 1 | Construction of culverts & drains in Nugepola Dehenakanda road (2.00-3.00Km) | 3 | [5 empty] | Ratnapura
|  | 2 | Contruction of side walls & shoulders of Mudduwa Niralgama Alupotha road(0.00-3.00Km) | 5.5 | [5 empty] | Ratnapura
|  | 3 | Construction of culverts & drains in Madala Karadana road (0.00-11.00Km) | 3 | [5 empty] | Eheliyagoda
|  | 4 | Construction of culverts, side walls & shoulders in Kadangoda Theppanawa road (0.00-3.00Km) | 5 | [5 empty] | Kuruwita
|  | 5 | Construction of culverts in Hamgamuwa Karawita road | 8
|  | 6 | Construction of drain & shoulders in Ellagawa Dumbara road (2.20-4.20Km) | 8
|  | 7 | Construction of necessary culverts & bridge in access road for Wawulpana Tourist Attraction Place. | 8
|  | 8 | Construction of wall at 1.5Km position in Udumulla Heenatipana Kanda road |  | 6 |  |  |  |  | Mawanella
|  | 9 | Construction of side wall at 5.900Km position in Ganethenna Kowilkanda road |  | 3 |  |  |  |  | Mawanella
|  | 10 | Contruction of side walls & shoulders in Dippitiya Hemmathagama road |  | 3.6 |  |  |  |  | Aranayaka
|  | 11 | Construction of drain & shoulders in Thalagolla Golden Bridge road |  | 7 |  |  |  |  | Mawanella
|  | 12 | Construction of drain & shoulders in Thaldewa Hangawela road |  | 7 |  |  |  |  | Rambukkana
|  | 13 | Construction of drain & shoulders in Hureemaluwa Kurempola Pinnawala road |  | 4 |  |  |  |  | Rambukkana
|  | 14 | Construction of drain & shoulders in Aranayaka Keli road |  | 7 |  |  |  |  | Aranayaka
|  | 15 | Construction of two culverts & drain in Ukgoda Theleka Madiliya road |  | 5 |  |  |  |  | Aranayaka
|  | 16 | Construction of culvert at 1.20Km position in Menama Ambadeniya Weragoda road |  | 3 |  |  |  |  | Aranayaka
|  | 17 | Construction of side wall Sudugala Arewepola road |  | 3 |  |  |  |  | Aranayaka
|  | 18 | Construction of drain & shoulders in Udawewala Kandewaththa road |  | 4 |  |  |  |  | Aranayaka
|  | 19 | Construction of side wall at Madagoda Meethirigala road |  | 4 |  |  |  |  | Ruwanwella
|  | 20 | Construction of necessary side walls & drain system at Amithirigala Hissella road |  | 4 |  |  |  |  | Ruwanwella
|  | 21 | Construction of necessary side wall Galapitamada Athaudakanda road |  | 5 |  |  |  |  | Ruwanwella
|  | 22 | Construction of drainage system in necessary places & shoulders in Deraniyagala Yatiwala road |  | 8 |  |  |  |  | Deraniyagala
|  | 23 | Construction of retaining wall & drain system in Deraniyagala Demada road via Kuruwita |  | 4 |  |  |  |  | Deraniyagala
|  | 24 | Construction of necessary retaining walls in Deraniyagala Yatiwala road |  | 5 |  |  |  |  | Deraniyagala
|  | 25 | Construction of drain system in necessary places in Garagoda Meegasthenna road |  | 4 |  |  |  |  | Yatiyanthota
|  | 26 | Construction of drain system in necessary places & retaining wall in Kithulgala Maiwaththa road |  | 4 |  |  |  |  | Yatiyanthota
|  | 27 | Construction of drain system in necessary places & retaining wall in Magammana old railway station road |  | 5 |  |  |  |  | Yatiyanthota
|  | 28 | Construction of drain system in necessary places in Pannila Miththragama road |  | 4 |  |  |  |  | Dehiowita
|  | 29 | Construction of drain system in necessary places in Algoda Dangampala road |  | 5 |  |  |  |  | Dehiowita
|  | 30 | Construction of shoulders in necessary places & drain system in Welihinda Handurukanda road (0.00-5.50Km) - 2nd stage | 8
|  | 31 | Construction of shoulders in necessary places & drain system in Godakawela werahera road (0.00-2.50Km) | 5
|  | 32 | Construction of drain system in necessary places & shoulders in Pelmadulla Kuttapitiya Waththepanguwa road | 2
|  | 33 | Construction of drain system in necessary places & shoulders in Godakawela Masimbuala road | 2
|  | 34 | Construction of drain system in necessary places & shoulders in Morathota Ketethenna road | 2
|  | 35 | Construction of drain system near Udagama junction in Udawela Akarella road | 1
|  | 36 | Construction of culvert at 7.3Km position & construction of drain system in Kahawaththa Manandola Endana road | 7.5
|  | 37 | Construction of culvert at 3.00Km position in Yainna Bungiriya road | 0.5
|  | 38 | Constrction of side walls at 4.00 - 5.00Km in Alpitiya amatiyagoda Redeewita road | 2
1.3 Road safty improvement - 14.00 | 1.3.1. Accident mitigation settings.(Rs.Mn 6.00 ) | 1 | Constructing side walls in dangerous places of Kalugala Arachchikumbura road | 6
| 1.3.2. Sign board(Rs.Mn 4.00 ) | 2 | Construction of sign board in selected provincial roads | 4
| 1.3.3. Pedestrian crossing(Rs.Mn 4.00 ) | 3 | Marking Pedestrian crossing in necessary places in provincial roads | 4
1.4. Reconstuction of major structures (Rs.Mn 29.00) | 1.4. Renovation of major structures (Rs.Mn 29.00) | 1 | Reconstruction of culverts of Kehelowitigama Kohombakanda road (0.00-2.00Km) | 3 |  |  |  | Rath E.E | n | Ratnapura
|  | 2 | Expanding culverts & constructing shoulders in Weralupa Kospelawinna road (1.00-3.00Km) | 3 | [5 empty] | Ratnapura
|  | 3 | Reconstructing culverts of Kosgala Kithulpe road (0.00-3.00Km) | 3 | [5 empty] | Ratnapura
|  | 4 | Expanding culverts of Getaheththa Karadana road (0.00-6.00Km) | 3 | [5 empty] | Eheliyagoda
|  | 5 | Expanding culverts of Kohiladeniya Medikele road (0.00-3.00Km) | 3 | [5 empty] | Eheliyagoda
|  | 6 | Expanding culverts & constructing shoulders in halpe Gorakaela road (0.00-3.00Km) | 4 | [5 empty] | Kuruwita
|  | 7 | Reconstruction of bridge at 1.5Km position in Paththampitiya Natiyapana road | 0 | 4 |  |  |  |  | Rambukkana
|  | 8 | Expanding bridge at Akarella junction in Udawela Akarella road | 2
|  | 9 | Expanding road using concrete side wall between 1.00 to4.00Km in Udawela Akarella road | 2
|  | 10 | Expanding bridge at starting point in Goadakawela Masimbula road | 2
SubTotal |  |  |  | 340 | 215.6 |  |  |  |  | 555.6
Enhansment of Planing and Management
2.2 maintaining existing capital assets & provision of new assets - 5.00 | 2.2.1. Purchasing equipment 5.00 | 1 | Purchasiing Laptop Computers for Executive Engineering offices and Diputy Director Offices | 0.9 | 0.6 |  |  | Bala E.E
|  | 2 | Purchasing plants, machinery & equipments for road development | 1.3 | 1
|  | 3 | Purchasing equipments for ministry | 0.7 | 0.5
Sub total |  |  |  | 2.9 | 2.1
Total |  |  |  | 342.9 | 217.7
Grand total |  |  |  | 560.6

## Form 4
Form 04
Department/Agency: Ministry of Provincial Roads Development, Rural Infrastructure, Tourism, Sports and Youth Affairs
Sector -Provincial Roads
Amounts required for continuation work and bills in hand - 2021
Project | Year commenced | Total Estimated cost (Rs. Mn) | Cumulative expenditure as at 31.12.2020(Rs. Mn) | Amount for 2021 (Rs. Mn)
|  |  |  | Bills in Hands | continuation work | Total
Provincial Roads | 2020 | 201.36 | 120.89 | 5.2 | 34.2 | 39.4
Summary of the annual budget
Amount required for new work as per form 03 - PSDG |  |  |  |  | 560.6
Amount required for continuation work and bills in hand - PSDG |  |  |  |  | 39.4
Total |  |  |  |  | 600